## Sheet1
|  | Project Name: | To - Do List Application
|  | Project Description: | Designing a full stack todo list web app.
|  | Project Owner: | Andi Berisha
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 01.12.21 | Covid-19 | The pandemic may prevent |  | x |  | x |  | Could impede productivity in regards to the project due to the toll on physical and psychological health which the pandemic may take. | Entire Length of Project | 10 minute meditation and an hour of physical exercise everyday to protect and improve mental and physical well being.
2 | 01.12.21 | Ankle Injury | As I broke my ankle 2 months prior to the start of the academy, so if I do not adhere to a strict physio-routine. I may encounter pain which may impede my focus and project progress. | x |  |  | x |  | If the proper precautions are not taken the project could be affected significantly as several days and maybe weeks would have to be taken off to deal with and manage the pain. | Entire Length of Project | The adherence to a strict physio-routine and also a check in with a physiotherapist every 2 weeks.
3 | 01.12.21 | Carpal Tunnel | Pressure on the median median nerve causing it to compress and thus leading to weakness in the hands. In this case this would be caused by heavy keyboard use. | x |  | x |  |  | Would obstruct the ability to work and think freely due to the constant hand pain. | Entire Length of Project | Frequent rest breaks and hand stretching routines.
4 | 01.12.21 | Neck and back muscle strains. | Poor sitting posture habits whilst using the computer can lead to these strains, thus resulting in a degredation of posture. | x |  | x |  |  | None but it would affect the health of the project participant in the longterm. | Entire Length of Project | Adjusting the height of the monitor to ensure the best possible posture while seated.
5 | 5.02.21 | Migraines and Eye Strains | Prolonged usage of the pc without any adequate breaks could lead to distruptive migraines and eye strains. |  | x |  |  | x | If the proper precautions are not taken the project could be affected significantly as several days and maybe weeks would have to be taken off to deal with and manage the pain. | Entire Length of Project | The use of a monitor with a blue light filter, many computer breaks and adequate migraine medications will be employed to prevent and mitigate this risk.
6 | 5.02.21 | Personal Problems | Relationship and home problems which may impede project progress. |  | x |  |  | x | Could impede productivity as focus may be heavily impeded due to factors such as depression and anxiety. | Entire Length of Project | Setting up bi-monthly meetings with a therapist to ensure optimum mental health.
7 | 5.02.21 | Internet Access | Internet outages may lead to lack of internet access. | x |  |  |  | x | This would severly impact course progress. | Entire Length of Project | Use the laptop provided by QA alongside my PC so in the worst case scenario my phone could be used as a internet hotspot and thus I can continue with the project on my laptop.
8
9
10